## Gantt Chart
PROJECT TITLE | [24 empty] | SHAIK SIDDIK
Phase Number | TASK TITLE | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [9 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [9 empty] | PHASE FIVE
[6 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
1 | Project Planning and Initiation
1.1 | Finalize research title and objectives | 2025-01-04 | 2025-03-04 | 3 | 100% | bar: WEEK 1 M to WEEK 1 W
1.2 | Conduct initial review of literature | 2025-04-04 | 2025-06-04 | 3 | 100% | bar: WEEK 1 Th to WEEK 2 M
1.3 | Prepare proposal and project plan | 2025-07-04 | 2025-09-04 | 3 | 100% | bar: WEEK 2 T to WEEK 2 Th
1.4 | Get supervisor approval | 2025-10-04 | 2025-11-04 | 2 | 100% | bar: WEEK 2 Th to WEEK 2 F
2 | Literature Review & Secondary Data Collection
2.1 | Conduct an in-depth literature review | 2025-12-04 | 17/4/2025 | 6 | 100% | bar: WEEK 3 M to WEEK 4 M
2.2 | Identify themes related to barriers/enablers | 18/4/2025 | 21/4/25 | 4 | 100% | bar: WEEK 4 T to WEEK 4 F
2.3 | Collect and organize secondary data (reports, papers) | 22/4/25 | 27/4/25 | 6 | 100% | bar: WEEK 4 F to WEEK 5 F
3 | Data Analysis
3.1 | Thematic analysis of secondary data | 28/4/25 | 2025-02-05 | 5 | 100% | bar: WEEK 6 M to WEEK 6 F
3.2 | Identify major patterns and insights | 2025-03-05 | 2025-06-05 | 4 | 100% | bar: WEEK 7 M to WEEK 7 Th
3.3 | Relate findings to reflective learning framework | 2025-07-05 | 2025-10-05 | 4 | 100% | bar: WEEK 8 M to WEEK 8 F
4 | Drafting Findings & Discussion
4.1 | Draft findings chapter | 2025-11-05 | 14/5/25 | 4 | 100% | bar: WEEK 9 M to WEEK 9 Th
4.2 | Link findings with literature and research objectives | 15/5/25 | 18/5/25 | 4 | 100% | bar: WEEK 9 F to WEEK 10 W
4.3 | Draft discussion section | 19/5/25 | 22/5/25 | 4 | 100% | bar: WEEK 10 T to WEEK 10 F
5 | Finalization
5.1 | Write introduction, methodology, and conclusion | 23/5/25 | 26/5/25 | 4 | 100% | bar: WEEK 11 M to WEEK 11 Th
5.2 | Compile references, appendices, ethical declarations | 27/5/25 | 29/5/25 | 3 | 100% | bar: WEEK 11 F to WEEK 12 T
5.3 | Proofreading, formatting, and submission | 30/5/25 | 1//6/25 | 3 | 100% | bar: WEEK 12 W to WEEK 12 F